## Dashboard
Project Name: Office Green - Plant Pals Operations and Training project
Description: Office Green, LLC, is a commercial landscaping company that specializes in plant decor for offices and other businesses. The company is getting ready to introduce its new Plant Pals service, which will provide high-volume customers with small, low-maintenance plants for their desks. Office Green’s main goal for this project is: “Increase revenue by 5% by the end of the year by rolling out a new service that provides office plants to high-volume clients.”
Owner: Angela Brown, PM
Status: Draft/Active/Inactive
Key Docs | Description
Project charter | Office Green - Plant Pals Project Charter | An overview of the project, key elements and expectations
Statement of work | Office Green - Plant Pals SoW | Identifies the work that is included in the project and the pricing that was quoted initially.
Risk management plan | Office Green - Plant Pals RMP | Identifies the potential risks to the project, their likelihood, and how you plan to mitigate them if they become realized.
Schedule | Office Green - Plant Pals Project Schedule | Identifies the planned schedule as well as any changes through out the project lifecycle.
Budget | Office Green - Plant Pals Budget | Identifies the planned budget as well as any over and under runs. Allows you to estimate the cost at completion.
Communication plan | Office Green - Plant Pals Communication Plan | Identifies how often, what type of communication method, and what information your stakeholders needs to know
Shared folder | Office Green Plant Pals - Google Drive | Folder with all relevant documentation
RACI chart | Office Green - Plant Pals RACI Chart | Identifies who is responsible, accountable, consulted and informed within the project.

## Project Schedule
Gantt Chart
TITLE: Plant Pals Operations and Training Plan | [6 empty] | COMPANY NAME: |  |  |  |  | Office Green
PROJECT MANAGER: Angi Brown | [6 empty] | CREATION DATE: |  |  |  |  | 02/15
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Establish a plant delivery and logistics plan | [5 empty] | 100% | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Source packaging materials | Fulfillment Director | 3/1 | 3/12 | 12 | 0% | bar: MARCH M 100% to MARCH F 12
1.2 | Hire delivery drivers | Human Resources Specialist | 3/15 | 3/26 | 10 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Calculate the delivery fees | Financial Analyst | 3/29 | 4/29 | 30 | 0% | bar: MARCH M 29 to APRIL R 29
2 | Select and install supply chain software
2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory Manager | 4/12 | 4/14 | 3 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Supervise vendor installation of the fulfillment equipment | Fulfillment Director | 4/15 | 4/16 | 2 | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Determine internal safety protocols for equipment | QA Tester | 4/19 | 4/30 | 11 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Develop and launch an employee training program
3.1 | Develop training sessions | Human Resources specialist | 5/3 | 5/14 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Train employees to use the software and equipment | Training Manager | 5/17 | 5/28 | 10 | 0% | bar: MAY M 17 to MAY F 28
3.3 | Monitor employee progress and improve training processes | Training Manager | 5/31 | 6/11 | 10 | 0% | bar: MAY M 31 to JUNE F 11

## Budget
Budget: Project Plant Pals Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | 62000 | 0 | 62000
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Establish a plant delivery and logistics plan.
Task 1: Purchase delivery trucks |  |  |  | 2 | 15000 |  | 30000 |  | -30000
Task 2: Source packaging materials. |  |  |  | 1500 | 2 |  | 3000 |  | -3000
Task 3: Pay delivery drivers. | 2 delivery drivers | 160 | 15 |  |  |  | 2400 |  | -2400
-- | [5 empty] | Total | 35400 | 0
Milestone 2: Select and install supply chain management software and equipment.
Task 1: Source vendor | [5 empty] | 15000 | 15000 |  | -15000
-- | [5 empty] | Total | 15000 | 0
Milestone 3: Develop and launch an employee training program.
Task 1: Develop training sessions | HR Specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 2: Train employees to use software and equipment. | Training manager | 80 | 25 |  |  |  | 2000 |  | -2000
Task 3: Monitor employee progress and improve training processes. | Training manager | 80 | 25 |  |  |  | 2000 |  | -2000
-- | [5 empty] | Total | 8000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 62000 | 0

## Communication Plan
Project Plant Pals: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings.
Software and Equipment Vendor | Planning Meeting | One time | Core Team: HR Specialist & Training Manager | One-time meeting before end of vendor's SoW, May 31 @ 12pm-4pm | In Person | Go over the training manual in order to create an effective training plan for Office Green's employees | [link to vendor SoW] | This meeting needs to take place before the end of the vendor's SoW. Make sure the HR Specialist & Training Manager check in with fulfillment and inventory team members about the outcome of the meeting.
Human Resources | Planning Check-In | Weekly | Core Team: HR Specialist | Every Monday morning at 11am, send reminders the day before | In Person | Project planning assistance; provide support during the training session |  | Additional communication on an as-needed basis
Facilities | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Every Tuesday morning at 11am | Phone Call | Reserve rooms, spaces, and equipment needed for employee training | [link to room and equipment reservation form]
Print Shop | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Every Wednesday at 10am, including day before the event | Phone Call | Coordinate on the printing and delivery of training manuals for employees | [link to printing order form]
Office Green employees | Informational Update | Weekly | Core Team: Training Manager | Every Monday | Email (from company address) | Communicate schedules, locations, and other necessary details to trainees | [trainee email list] | Set up automated reminder emails
Office Green employees | Training | Daily | Core Team: Training Manager | 10 days, daily | In Person | Train employees to use the supply chain management software and equipment | [link to training schedule]
Office Green employees | Survey | One time | Core Team: Training Manager | May 31st @ 10am | Email (from company address) | Post-training survey | [trainee email list] | Discuss results at next team meeting
Your Manager | Status Update | Weekly | Project Manager | Mondays at 12pm | In Person | Update on event planning, ask questions, and get feedback |  | Come prepared with a brief update and specific questions
Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | One time | Project Manager | June 7 at 12pm | Email (from individual address) | High-level information and general updates | [link to folder with training notes and survey results]

## RACI Chart
R - Responsible | Completes the deliverable or task.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken.
I - Informed | Kept up to date on decisions made.
Plant Pals Landing Page | Web Manager | Graphic Designer | Web Developer | Quality Assurance Tester | Content Writer | Web Designer
PHASE 2
Task/Deliverable
1. Design a landing page | A | C | I | I | I | R
2. Create a landing page mockup | A | C | C | I | C | R
3. Design assets | R | I | I | I | I | A
4. Write content | A | I | I | I | R | I
5. Code the landing page | A | I | R | I | I | I
6. Test the landing page | A | I | I | R | I | I